## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56
Planning | 1 | 14 | 1 | 13 | 100%
Functions | 1 | 6 | 1 | 6 | 100%
Classes | 1 | 56 | 1 | 56 | 100%
Variables | 1 | 5 | 1 | 5 | 100%
DEVELOPMENT | 15 | 35 | 15 |  | 5%
Main Menu / Settings | 15 | 5 | 15 | 7 | 100%
Options Menu | 15 | 7 | 15 | 6 | 100%
Gameplay options | 15 | 7 | 15 | 5 | 100%
Exit function | 15 | 6 | 15 | 5 | 100%
Testing | 15 | 1 | 15 | 2 | 100%
Board Generation | 22 | 14 | 22 |  | 10%
Display empty board | 22 | 5 | 22 |  | 25%
Determine first player | 22 | 3 |  |  | 0%
Testing | 22 | 2 |  |  | 0%
Deployment | 30 | 7 |  |  | 0%
Show unplaced pieces | 30 | 7 |  |  | 0%
Determine legal deployment cells | 30 | 6 |  |  | 0%
Alternate players placing | 30 | 6 |  |  | 0%
End deployment | 34 | 7 |  |  | 0%
Testing | 34 | 5 |  |  | 0%
Player Movement | 36 | 7 |  |  | 0%
Determine legal moves | 1 | 2 |  |  | 0%
Update piece position | 36 | 5 |  |  | 0%
End turn function | 36 | 5 |  |  | 0%
Alternate player turns | 36 | 6 |  |  | 0%
Testing | 40 | 2 |  |  | 0%
Player Attacks | 43 | 7 |  |  | 0%
Determine legal attacks | 43 | 1 |  |  | 0%
Resolve combat | 43 | 7 |  |  | 0%
Remove losing piece(s) | 46 | 4 |  |  | 0%
Testing | 48 | 2 |  |  | 0%
Endgame | 48 | 8 |  |  | 0%
Check for draw conditions | 48 | 6 |  |  | 0%
Check for win conditions | 48 | 6 |  |  | 0%
End game | 48 | 6 |  |  | 0%
Declare winner or draw | 50 | 2 |  |  | 0%
Show pieces lost by player | 50 | 4 |  |  | 0%
Testing | 51 | 4 |  |  | 0%
Launch | 56 | 1 |  |  | 0%